## Progress Planning and Track
Project Name: | Green SP-27 Spotify Mobile App
Report Date:
[5 empty] | Milestone #1 |  |  |  | Milestone #2 |  |  |  | Milestone #3 |  |  |  | C-Day
Phase | Tasks | Complete% | Current Status Memo | Assigned To | 2016-09-02 | 2016-09-09 | 2016-09-16 | 2016-09-23 | 2016-09-30 | 2016-10-07 | 2016-10-14 | 2016-10-21 | 2016-10-28 | 2016-11-04 | 2016-11-11 | 2016-11-18 | 2016-11-25 | 2016-12-02
Requirements | Define requirements | 0% |  | Team | 2016-09-02: 10
| Get sign off on requirements | 0% |  | Team | 2016-09-02: 15
Project design | Define tech required * | 0% |  | Marc/Brian | 2016-09-09: 25; 2016-09-16: 10
| Develop working prototype | 0% |  | Marc/Brian | 2016-09-16: 15; 2016-09-23: 20; 2016-09-30: 15; 2016-10-07: 15; 2016-10-14: 10
| Test prototype | 0% |  | Jace | 2016-09-30: 10; 2016-10-07: 10; 2016-10-14: 5; 2016-10-21: 5; 2016-10-28: 5
Development | Review prototype design | 0% |  | Team | 2016-10-14: 5; 2016-10-21: 5; 2016-10-28: 5
| Rework requirements | 0% |  | Team | 2016-10-14: 5; 2016-10-21: 5; 2016-10-28: 5; 2016-11-04: 5; 2016-11-11: 5
| Document updated design | 0% |  | Muhammed | 2016-10-21: 5; 2016-10-28: 5; 2016-11-04: 5; 2016-11-11: 5
| Test product | 0% |  | Jace | 2016-10-21: 5; 2016-10-28: 10; 2016-11-04: 15; 2016-11-11: 10
Final report | Presentation preparation | 0% |  | Team | 2016-11-18: 15; 2016-11-25: 10; 2016-12-02: 10
| Poster preparation | 0% |  | Team | 2016-12-02: 10
| Website Creation | 0% |  | Muhammed/Jace | 2016-11-25: 5; 2016-12-02: 5
| Final report submission to D2L and project owner | 0% |  | Team | 2016-12-02: 5
|  |  | Total work hours | 330 | 25 | 25 | 25 | 20 | 25 | 25 | 25 | 25 | 30 | 25 | 20 | 15 | 15 | 30
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours